## Slide 1
PROJECT CHARTER · PROJECT PLAN · WBS & SCHEDULE
FoodShare Food Bank
Network Capacity & Efficiency Expansion Project
Project Number FSFB-2026
Scarborough · Mississauga · North Bay Hub Network
Prepared for Seneca Polytechnic — Business Information Technology Program
Sponsoring Organization: FoodShare Food Bank | July 23, 2026
Dev Patel · Ebuka · Vishal · Rui Song · Om Surani · Hirva · Maharshi Darji
PROJECT TEAM
Notes: Title slide. FoodShare Food Bank Management System — replacing spreadsheets and paper logs across three hubs with one integrated system covering donations, warehousing, inventory, transportation and distribution.

## Slide 2
What This Deck Covers
01
The Case for the Project
Background, business problem, purpose and objectives
02
Scope & Operating Model
In / out of scope, collection, warehousing, distribution, transport
03
People & Plan
Stakeholders, team roles, phased timeline, deliverables
04
Reference Benchmarks
Care Shield Food Bank operating data and what it means for us
05
WBS, Schedule & Cost
Work breakdown, MS Project baseline, resources and budget
06
Governance
Assumptions, constraints, risks, success criteria, next steps
Notes: Six sections: the case, the operating model, people and plan, benchmark data, the WBS and schedule from MS Project, and governance.

## Slide 3
Executive Summary
One system to replace the spreadsheets and paper logs running three hubs
3
Warehouse hubs
Scarborough, Mississauga, North Bay
2
Delivery trucks
Pickup, inter-hub transfer, distribution
9
Functions in scope
Donors through to reporting
5
Delivery phases
Requirements to Year 1 evaluation
The problem in one line
Grocery stores, restaurants and farms already have surplus food that is safe to eat. FoodShare exists to move it to registered families before it expires.
Today that runs on manual records — which means missed entries, inventory counts that drift from reality, and food sitting in storage past the point it should have gone out the door.
What makes this charter different
Rather than guessing at what a mature three-hub network looks like operationally, we pulled the publicly available operating figures from Care Shield Food Bank — a comparable Scarborough / Mississauga / North Bay network — and used them as reference benchmarks (Section 14).
A same-size network's real numbers give us far more grounded planning assumptions than we would have reached on our own.
Notes: Executive summary. The system covers donations, warehousing, inventory, transportation and distribution. Benchmarks come from Care Shield Food Bank, used strictly as a planning comparison.

## Slide 4
Background & Business Problem
Sections 2 and 4 — why the current way of working stops scaling
The gap FoodShare sits in
Food insecurity has been climbing as living costs outpace what many households can absorb. At the same time a surprising amount of usable food never reaches anyone — stores and restaurants routinely discard items close to their best-before date that are still perfectly fine to eat. FoodShare collects that surplus, stores it properly, and gets it to families before it spoils.
What has not kept pace
The organization already runs three hubs, but the process behind the scenes has not kept up with the volume it now handles. Layer three warehouses, a rotating delivery schedule and varying family requirements on top of manual records, and it becomes genuinely hard to know what food is on hand and who is next in line for it — so distribution decisions get made on an incomplete picture.
How manual records break down
Records go missing
Donations entered on paper or in one person's spreadsheet never reach the shared record
Counts stop matching the shelf
Inventory drifts from physical stock, so staff plan against numbers that are already wrong
Food quietly expires
Items sit in storage because nobody flagged the expiry date in time
No single view of the network
Three warehouses, a rotating schedule and varying family needs, with nothing tying them together
Notes: Section 2 and 4 of the charter. The four failure modes on the right are the specific, predictable ways manual record-keeping breaks down at this scale.

## Slide 5
Project Purpose & Objectives
Sections 3 and 5 — one system, seven measurable objectives
PURPOSE Give FoodShare a single system for managing food donations from its partners and getting that food out to registered families fairly and on time — cutting food waste, tightening inventory accuracy, and making the donation-to-distribution pipeline something the organization can run predictably rather than reactively.
01
One central database
Covering all food donations across the network
02
Accurate inventory
Tracked across all three warehouses
03
Donors & families in one place
Single maintained record for each
04
Cut food waste
Prioritize items closest to expiry (FIFO)
05
Schedule collection & distribution
Pickup runs and monthly distribution
06
Reports at a glance
Staff monitor inventory and donations directly
07
Better partner communication
Between FoodShare and its partner organizations
Notes: Purpose from Section 3, the seven objectives from Section 5 of the charter.

## Slide 6
Project Scope
Section 6 — nine functions in, six explicitly out
IN SCOPE
Donor registration
Family registration
Food donation records
Inventory management
Management of all three warehouses
Transportation management
Monthly food distribution schedule
Food collection scheduling
Reporting on inventory and donations
OUT OF SCOPE
Cash donations
Online payment processing
International food distribution
Clothing donations
Medical services
Disaster relief programs
FoodShare accepts food items only — not money. Anything outside the donation-to-distribution pipeline is deliberately excluded to keep the build deliverable in one semester.
Notes: Scope boundaries from Section 6. The out-of-scope list matters as much as the in-scope list for a one-semester build.

## Slide 7
How the System Will Work
Section 7 — food reaches FoodShare through two channels
METHOD 1 — PICKUP FROM PARTNER LOCATIONS
1
Partner logs in
Grocery stores, restaurants, farms and community organizations use the FoodShare portal
2
Donation entered
Item, quantity, expiry date and food category are submitted
3
Pickup scheduled
The donation joins the pickup schedule for that hub
4
Truck collects
One of FoodShare's two trucks picks it up on schedule
METHOD 2 — DIRECT WAREHOUSE DROP-OFF
1
Donor arrives
Food is brought straight to one of the three warehouses
2
Staff inspect
Quantity, expiry date, category and packaging condition are checked
3
Details corrected
Anything the donor entered incorrectly is fixed before logging
4
Inventory updated
The record is created and the food moves into storage
Notes: Two collection channels: scheduled pickup from partner locations, and direct drop-off at a warehouse. Both end in the same place — a verified inventory record.

## Slide 8
Warehouse Process & the Hub Network
Sections 8 and 11 — every donation is inspected before it becomes stock
Inspection on arrival
Quantity
Expiry date
Food category
Packaging condition
Staff correct any information the donor entered incorrectly before it is logged into inventory. Perishable items go into refrigerated storage as needed.
Every warehouse also holds
Refrigerated storage for dairy and other temperature-sensitive items
A small safety stock set aside for emergencies or unexpected spikes in demand
Three warehouse hubs
Scarborough
Refrigerated storage · safety stock
32.6%
of families (benchmark)
Mississauga
Refrigerated storage · safety stock
32.2%
of families (benchmark)
North Bay
Refrigerated storage · safety stock
35.2%
of families (benchmark)
Hub share figures are Care Shield benchmark values (Section 14.1), used as a planning reference.
Notes: Warehouse process from Section 8; the hub network from Section 11. Hub percentage split comes from the benchmark network, not from FoodShare's own data.

## Slide 9
Food Distribution Process
Section 9 — First In, First Out, with packages built around each household
FIFO
First In, First Out
Whatever comes in first goes out first. That keeps waste down and means families consistently receive fresher food rather than whatever happens to be easiest to reach. Perishable food is always distributed first.
Package assembly
Families are registered before they receive anything
Packages are put together based on family size and monthly need
Food is distributed once every month to registered families
What a family record holds
Family ID
Unique identifier for the household
Address
Hub assignment and delivery routing
Household size
Drives package size and contents
Ages
Adults, children and seniors in the household
Food allergies
Excluded items flagged at packing
Notes: FIFO distribution from Section 9. Note the charter also refers to FEFO tracking in Section 14.7 — worth confirming which term the sponsor wants used throughout.

## Slide 10
Transportation
Section 10 — two trucks doing three jobs
1
Pick up donations
Collect from partner grocery stores, restaurants, farms and community organizations on the pickup schedule
2
Move food between warehouses
Rebalance stock across the three hubs when one runs full or short
3
Support distribution runs
Deliver assembled monthly packages to registered families
Route classification
< 50 km
SHORT HAUL
50 km +
LONG HAUL
Fleet constraint
FoodShare currently runs two delivery trucks, and the plan assumes both remain available throughout the project. That is a real ceiling on how much can be collected and delivered in a week — which is why route balance across the three hubs is treated as a design question now rather than an operational surprise later.
Notes: Two trucks, three functions, and a 50 km short-haul / long-haul split. Fleet size is one of the project's stated constraints.

## Slide 11
Stakeholders
Section 12 — nine groups with a stake in the outcome
Project Sponsor
Approves and supports the project
Project Manager
Plans and manages the project
Warehouse Manager
Manages warehouse operations
Warehouse Staff
Inspect and store donations
Delivery Drivers
Collect donated food
Volunteers
Help with sorting and packaging
Donors
Donate food items
Registered Families
Receive food assistance
Community Partners
Provide food donations and collection points
Notes: Nine stakeholder groups and their responsibilities, from Section 12 of the charter.

## Slide 12
Team Structure & Roles
Section 13.1 — a named lead per area keeps ownership clear
DP
Dev Patel
Project Manager
Overall coordination, schedule, and sponsor liaison
E
Ebuka
Systems Analyst
Requirements gathering and process mapping
V
Vishal
Database Developer
Database design for donations, inventory, and family records
OS
Om Surani
QA & Testing Lead
Test planning and defect tracking
MD
Maharshi Darji
Business Analyst
Business case, benchmarking, and reporting
RS
Rui Song
UI/UX Designer
Portal and dashboard screens for staff and partners
H
Hirva
Documentation Lead
Charter, user guides, and meeting records
In practice everyone contributes across areas — this is a seven-person team building a full system in one semester.
Notes: Seven named leads. The note bottom-right is verbatim from the charter — roles are ownership markers, not hard silos.

## Slide 13
Timeline & Milestones
Section 13.2 — five phases running Q3 2026 through Q3 2027
1
Q3 2026
Requirements
& Planning
Confirm scope with FoodShare staff; finalize the database schema for donations, inventory and family records; validate assumptions against warehouse and truck data.
2
Q3–Q4 2026
Design &
Core Database
Build the central database; design the donor and family registration modules; set up warehouse and inventory data structures.
3
Q4 2026–Q1 2027
Module
Development
Develop the donation portal, inventory management, transportation scheduling and FIFO-based distribution logic.
4
Q1–Q2 2027
Testing
& Pilot
Run integration and user-acceptance testing; pilot the system at one warehouse before network-wide rollout.
5
Q2–Q3 2027
Rollout, Training
& Evaluation
Roll out to all three hubs; train staff and volunteers; deliver reports and dashboard; compile a Year 1 evaluation.
Phased rollout mirrors the approach used by comparable food bank technology projects. A detailed working schedule is baselined in MS Project — see Section 5 of this deck.
Notes: The charter roadmap is quarter-level and runs Q3 2026 to Q3 2027. The MS Project file baselines a shorter, task-level working schedule for the build itself.

## Slide 14
Major Deliverables
Section 13.3 — nine artefacts handed over to FoodShare
1
FoodShare central database
One store for donations, inventory, donors and families
2
Donor management module
Registration and partner records
3
Family registration module
Household records, size, ages, allergies
4
Warehouse management module
Hub-level operations and storage
5
Inventory management module
Stock levels and reorder alerts
6
Transportation module
Pickup, transfer and delivery scheduling
7
Food distribution module
FIFO logic driving what goes out first
8
Reports and dashboard
Inventory and donation visibility for staff
9
User documentation & training
Guides and materials for staff and volunteers
Notes: Nine major deliverables from Section 13.3. Reports and dashboard are core deliverables rather than post-launch additions.

## Slide 15
SECTION 14
Reference Benchmarks
Care Shield Food Bank — a comparable three-hub network, further along in data maturity — gives us a realistic picture of what a network at this scale looks like once it is fully instrumented.
Notes: Divider into the benchmark section. FoodShare does not yet capture structured network-wide statistics — that is a large part of why this project exists.

## Slide 16
Benchmark: Families & Community Reach
Section 14.1 — what a fully instrumented network of this size supports
1,000
Registered families
4,557
Individuals supported
4.56
Average family size
45.0% / 35.5% / 19.5%
Adults / Children / Seniors
Chart: Registered families by hub
| North Bay | Scarborough | Mississauga
Registered families | 352 | 326 | 322
Reading the split
Demand is spread almost evenly across the three hubs — 35.2% / 32.6% / 32.2%. No single warehouse dominates, which means inventory visibility and route balance have to work equally well at all three sites rather than being tuned for a flagship location.
Source: Care Shield Food Bank operating data, used as a planning benchmark (Section 14).
Notes: 1,000 families, 4,557 individuals, average household 4.56 people. Near-even hub split is the key planning takeaway.

## Slide 17
Benchmark: Donor Network
Section 14.2 — 500 active donor locations across the three hubs
Chart: Donor locations by hub
| Mississauga 35.8% | North Bay 33.2% | Scarborough 31.0%
Donor share | 35.8 | 33.2 | 31
500
Total active donor locations
100% of them currently active
10.6%
Largest single donor brand
Two chains at 53 locations each
40%+
Pickups on two days
Wednesday and Friday are the busiest
Concentrating over 40% of pickups on Wednesday and Friday puts real pressure on a two-truck fleet — a scheduling constraint the transportation module has to handle explicitly.
Notes: 500 donor locations, evenly spread. Pickup-day concentration on Wednesday and Friday is the operational risk to design around.

## Slide 18
Benchmark: Inventory & Storage
Section 14.3 — 100 SKUs and 147,257 units on hand across four storage types
Chart: Stock on hand by storage type (units)
| Dry | Cold | Controlled (medical) | Frozen
Stock on hand (units) | 86964 | 24697 | 21028 | 14568
SKUs tracked
Dry
59
Cold
19
Controlled
13
Frozen
9
Total
100
6
Six of Care Shield's 100 tracked SKUs were running below reorder level when this data was captured — a reminder that reorder-alert logic, already planned as part of FoodShare's inventory module, earns its keep even at moderate scale.
Notes: Dry storage dominates at 59 SKUs and roughly 59% of units. Reorder alerts matter even at this scale — 6% of SKUs were below reorder level.

## Slide 19
Benchmark: Staffing, Transport & Collection
Sections 14.4 and 14.5 — the people and movement behind the numbers
7
Full-time staff
25–50
Active volunteers
2
Active delivery trucks
45.0
Avg crates collected / day
Operating pattern
Operating days
Monday – Saturday
Operating hours
08:00 – 16:00
Scheduled pickup-days (annual)
365
Total crates collected (annualized)
16,435
What it implies for FoodShare
Roughly 45 crates a day across two trucks and six operating days is the throughput a system at this scale has to record without becoming a bottleneck.
Volunteer numbers are an informal range rather than a headcount — volunteer availability is listed as a project constraint for exactly this reason.
Notes: Seven full-time staff, an informal 25-50 volunteer range, two trucks, ~45 crates a day, 16,435 crates a year.

## Slide 20
Benchmark: Annual Operating Budget
Section 14.6 — $693,160 CAD across ten categories
Chart: 
| Staff | Facility | Transportation | Operations | Contingency | Utilities | IT | Insurance | Marketing | Training
Annual cost (CAD) | 380000 | 180000 | 48500 | 21600 | 20000 | 18000 | 8060 | 8000 | 5000 | 4000
$693,160
Total annual operating budget (CAD)
Share of total
Staff
54.8%
Facility
26.0%
Transportation
7.0%
Operations
3.1%
Contingency
2.9%
Utilities
2.6%
IT
1.2%
Insurance
1.2%
Marketing
0.7%
Training
0.6%
Source: Care Shield Food Bank operating data. IT spend of $8,060 (1.2%) is the line this project most directly affects.
Notes: Staff and facility take 80.8% of the budget. IT is 1.2% — which sets a realistic ceiling on what FoodShare can spend running the system after handover.

## Slide 21
What the Benchmarks Mean for FoodShare
Section 14.7 — design for it now rather than discover it later
1
Same starting shape
FoodShare runs the same two-truck, three-warehouse setup Care Shield started with — so the pressures Care Shield hit are realistic early warning signs, not hypotheticals.
2
Known failure points
Uneven pickup-day coverage between hubs, and a handful of SKUs slipping below reorder level, are the two specific things to design around.
3
Core, not nice-to-have
That is why FEFO tracking, per-warehouse inventory visibility and a reporting dashboard are core deliverables rather than additions after launch.
The scale check
A mature three-hub network in this size range tends to land somewhere around a few hundred thousand units of inventory on hand and tens of thousands of crates moved per year. FoodShare's system needs to be built to comfortably handle that range of volume — not just the smaller numbers the organization is working with today.
~147K
units on hand
~16K
crates / year
Notes: Three takeaways plus the scale check: build for benchmark volumes, not today's numbers.

## Slide 22
WORK BREAKDOWN STRUCTURE
WBS, Schedule & Cost Baseline
Five work packages · 41 scheduled tasks · 456 hours of work · $25,010 in resource cost · 15 June to 4 August 2026
Notes: Divider into the WBS and schedule baselined in Microsoft Project, plus the WBS dictionary entries.

## Slide 23
Work Breakdown Structure
Five work packages decomposed to task level in Microsoft Project
DURATION
WORK
COST
2
Requirements & Analysis
Review spreadsheets · identify data entities · stakeholder workshops · document and validate requirements
5 d
48 h
$2,600
3
Database Design & Build
Logical and physical design · configure environment · implement tables and relationships · technical testing
11 d
168 h
$9,380
4
Data Migration
Assess data quality · clean and standardize · build import process · load and validate
3.5 d
72 h
$3,320
5
Reporting & Training
Identify and design reports · implement dashboard · UAT · user guides · training · handover
7.5 d
88 h
$4,990
6
Project Management
Initiation and kickoff · status reporting · risk and issue management · closure and lessons learned
9 d
80 h
$4,720
TOTAL · 41 scheduled tasks across 5 work packages
36.5 d
456 h
$25,010
Notes: Five work packages. Database Design & Build is the largest at 168 hours and $9,380 — over a third of total project cost.

## Slide 24
Project Schedule
Microsoft Project baseline — 15 June to 4 August 2026, 36 working days
15 Jun
22 Jun
29 Jun
6 Jul
13 Jul
20 Jul
27 Jul
3 Aug
Requirements & Analysis
15 Jun – 19 Jun
Database Design & Build
22 Jun – 6 Jul
Data Migration
7 Jul – 10 Jul
Reporting & Training
13 Jul – 22 Jul
Project Management
23 Jul – 4 Aug
Project closure & lessons learned — 4 Aug 2026
Finish-to-start throughout
Requirements are validated with the sponsor before database design begins; migration waits on technical testing of the structure.
Critical path
Project Management runs to the final task — closure and lessons learned on 4 August is the schedule-driving activity.
Sub-tasks decomposed
2.3, 3.1, 4.2 each break into three sub-tasks covering families, donors and inventory separately.
Notes: Schedule as baselined in the MPP file. Five phases run largely in sequence with finish-to-start dependencies.

## Slide 25
Resource Plan & Cost
Ten resources · 456 hours of assigned work · $25,010 total
Chart: 
| Project Manager | Database Designer | Developer | Business Analyst | Data Migration Lead | Tester / QA | Software License | Trainer | Travel & Meetings | Training Materials
Cost (CAD) | 7680 | 4400 | 4200 | 3400 | 2160 | 1120 | 1000 | 900 | 100 | 50
Standard rates
Project Manager
$60 / h
Database Designer
$55 / h
Business Analyst
$50 / h
Developer
$50 / h
Data Migration Lead
$45 / h
Trainer
$45 / h
Tester / QA
$40 / h
Training Materials
$25 / h
$25,010
Total resource cost (CAD)
Software License ($1,000) and Travel & Meetings ($100) are cost resources rather than hourly roles.
Notes: The Project Manager is the single largest line at $7,680 over 128 hours, reflecting the Project Management work package running the length of the schedule.

## Slide 26
WBS Dictionary
Twelve work packages documented in full — four shown here
2.1
Review existing spreadsheets and current data
Collect and examine all existing spreadsheets covering families, donors, inventory, transportation and weekly schedules. Review how data is structured, what fields are captured, and where inconsistencies, duplicates or gaps exist. Findings feed system requirements and later design and migration work.
3.1
Logical database design
Design the logical structure using approved requirements and identified entities: tables, fields, primary keys and relationships between families, donors, inventory items, hubs and routes — documented as entity-relationship diagrams and reviewed against core FoodShare operations.
4.2
Clean and standardize data
Check spreadsheet data for missing values, inconsistent formats, incorrect codes and duplicate records. Reformat addresses, phone numbers, status fields and item descriptions into consistent structures, producing a prepared data set that imports with fewer errors.
5.3
Implement reports / dashboard
Build the reports and dashboard views staff need: weekly distribution schedules, family lists by hub or priority, donor pickup schedules, and inventory status by category and location — connected to live tables and tested with sample data.
Full dictionary covers 2.1, 2.3, 2.4, 3.1, 3.1.1, 3.3, 4.2, 4.4, 5.3, 5.5, 5.6 and 6.2.
Notes: The WBS dictionary gives each work package a detailed description so scope is unambiguous at task level. Twelve entries in total.

## Slide 27
Assumptions & Constraints
Sections 15 and 16 — what we are taking as given, and what limits us
ASSUMPTIONS
FoodShare has three operational warehouses
Two delivery trucks are available throughout the project
Refrigerated storage is available for dairy and frozen products
Food donations are accepted only as food items, not money
Donors can request pickup or deliver food directly to a warehouse
Partner organizations will regularly update donation information through the portal
Warehouse staff will verify every donation before it is stored
Perishable food will always be distributed first using the FIFO method
Food is distributed once every month to registered families
Family food packages are prepared according to household size
Enough volunteers are available to support warehouse operations
CONSTRAINTS
Limited project budget
Only two delivery trucks are available
Limited warehouse storage capacity
Donations depend on community participation
Some food items have very short expiry dates
Volunteer availability may change throughout the year
Every constraint here has a matching risk on the next slide — the two lists are read together.
Notes: Eleven assumptions, six constraints. If any assumption fails — particularly truck availability or volunteer numbers — the schedule and scope need revisiting.

## Slide 28
Project Risks & Responses
Section 17 — six identified risks, each with a planned response
RISK
PLANNED RESPONSE
1
Food expires before distribution
Apply FIFO consistently and monitor expiry dates daily
2
Low number of donations
Build more partnerships with local businesses
3
Truck breakdown
Perform regular maintenance and keep a backup schedule
4
Inventory mistakes
Verify every donation before it is added to stock
5
Storage runs full
Move inventory between warehouses as needed
6
Uneven pickup coverage between hubs
Review route balance against per-hub demand, following the pattern observed in comparable networks (Section 14)
Notes: Six risks. The last one — uneven pickup coverage — was added specifically because the benchmark data flagged it as a real pattern in a comparable network.

## Slide 29
Success Criteria
Section 18 — how we will know the project worked
✓
Food donations are recorded correctly
✓
Inventory information stays accurate
✓
Food waste is reduced
✓
Families receive food on time
✓
Perishable food is distributed before expiry
✓
Warehouse operations become more organized
✓
Staff can generate reports whenever they are needed
Notes: Seven success criteria. They map back to the objectives in Section 5 — accurate records, reduced waste, timely distribution, and self-service reporting.

## Slide 30
Future Improvements
Section 19 — what this foundation makes possible next
1
More warehouse locations
Extend the hub network beyond the current three sites
2
A larger delivery fleet
Relieve the two-truck ceiling on collection and distribution
3
More community partners
Widen the donor base and add collection points
4
A mobile app
Give donors and volunteers a phone-first way to participate
The reporting layer is the multiplier
The reporting layer built in this phase would also let FoodShare start spotting donation trends and shifting family needs earlier — the same way the benchmark data in Section 14 has helped shape this plan. Once FoodShare's own donor, family and inventory data is captured independently, the organization can stop planning against someone else's numbers and start measuring itself.
Notes: Four future extensions plus the strategic point: the reporting layer turns a record-keeping system into a planning tool.

## Slide 31
References
Care Shield Food Bank. (n.d.). Care Shield Food Bank. Retrieved July 22, 2026, from csfoodbank.com.
Care Shield Food Bank. (2026). Food Bank Complete Database [Internal organizational dataset: Families, Donors, Costing, Inventory, Staff, Transportation, and Collection Schedule records].
Food Banks Canada. (n.d.). HungerCount report. Food Banks Canada.
Project Management Institute. (2021). A guide to the project management body of knowledge (PMBOK guide) (7th ed.). Project Management Institute.
This charter draws on Care Shield Food Bank's published operating figures strictly as a comparison benchmark for planning purposes. FoodShare's own donor, family and inventory data will be captured independently once the system described here is in place.
FoodShare Food Bank · Network Capacity & Efficiency Expansion Project · FSFB-2026
Seneca Polytechnic — Business Information Technology Program · July 23, 2026
Notes: References in APA format, plus the benchmark disclaimer from the charter.