PROJECT CHARTER & PROJECT PLAN

FoodShare Food Bank

Network Capacity & Efficiency Expansion Project

Project Number: FSFB-2026

Scarborough · Mississauga · North Bay Hub Network

Prepared for: Seneca Polytechnic — Business Information Technology Program

Sponsoring Organization: FoodShare Food Bank

Date: July 23, 2026

Team Members

Dev Patel

Ebuka

Vishal

Rui Song

Om Surani

Hirva

Maharshi Darji

# 1. Executive Summary

FoodShare Food Bank is putting together a Food Bank Management System to replace the spreadsheets and paper logs of its three hubs — Scarborough, Mississauga, and North Bay — currently rely on to track donations, inventory, and distribution. The idea is simple to state and harder to do well: grocery stores, restaurants, and farms already have surplus food that is safe to eat, and FoodShare exists to move that food to registered families before it expires, instead of letting it go to waste.

Right now, the organization runs on manual records. That works, but it also means missed entries, inventory counts that drift from reality, and food sitting in storage past the point where it should have gone out the door. This charter shows why the project matters, what it will and won't cover, how the day-to-day food flow will work once the system is live, and what the team plans to build and by when.

One thing this charter does differently from a typical student proposal: rather than guessing at what a mature three-hub network looks like operationally, we pulled in the publicly available operating figures from Care Shield Food Bank — a comparable Scarborough/Mississauga/North Bay food bank network — and used those as reference benchmarks (Section 9). FoodShare doesn't yet track things like SKU-level reorder points or route-days per hub in a structured way, so having a same-size network's real numbers to compare against gave us a much more grounded set of planning assumptions than we'd have arrived at on our own.

# 2. Project Background

Food insecurity has been climbing steadily as living costs outpace what a lot of households can absorb. At the same time, a surprising amount of usable food never reaches anyone — grocery stores and restaurants regularly discard items that are close to their best-before date but still perfectly fine to eat.

FoodShare's role is to sit in the middle of that gap: collect the surplus, store it properly, and get it to families who need it before it spoils. The organization already does this across three hubs, but the process behind the scenes hasn't kept pace with the volume it's now handling. This project builds the system to close that gap — a FoodShare Food Bank Management System covering donations, warehousing, inventory, transportation, and distribution, so volunteers and staff aren't reconstructing the same information by hand every week.

# 3. Project Purpose

The purpose of this project is to give FoodShare a single system for managing food donations from its partners and getting that food out to registered families fairly and on time. Beyond the day-to-day mechanics, the goal is to cut down food waste, tighten inventory accuracy, and generally make the donation-to-distribution pipeline something the organization can run predictably rather than reactively.

# 4. Business Problem

A lot of food banks, FoodShare included, still lean on manual records or spreadsheets for donations and inventory. That approach breaks down in predictable ways — records go missing, inventory counts stop matching what's actually on the shelf, and food quietly expires in storage because nobody flagged it in time.

Layer three warehouses, a rotating delivery schedule, and varying family requirements on top of that, and it gets genuinely hard to know what food is on hand and who's next in line for it. Without a system tying these pieces together, FoodShare is making distribution decisions with an incomplete picture.

# 5. Project Objectives

- Build one central database covering all food donations across the network.

- Track inventory accurately across all three warehouses.

- Maintain donor information and family records in one place.

- Cut food waste by prioritizing items closest to their expiry date.

- Schedule food collection and distribution runs.

- Produce reports that let staff monitor inventory and donations at a glance.

- Improve communication between FoodShare and its partner organizations.

# 6. Project Scope

## In Scope

- Donor registration

- Family registration

- Food donation records

- Inventory management

- Management of all three warehouses

- Transportation management

- Monthly food distribution schedule

- Food collection scheduling

- Report for inventory and donations

## Out of Scope

- Cash donations

- Online payment processing

- International food distribution

- Clothing donations

- Medical services

- Disaster relief programs

# 7. How the System Will Work

FoodShare collects food through two channels.

## Method 1 — Pickup from Partner Locations

Partner grocery stores, restaurants, farms, and community organizations log into the FoodShare portal and enter what they're donating: the item, quantity, expiry date, and food category. Once that's submitted, one of FoodShare's two trucks picks it up according to the pickup schedule.

## Method 2 — Direct Warehouse Drop-off

Donors can also bring food straight to one of the three warehouses. Warehouse staff inspect and verify the donation on arrival, then update inventory before it goes into storage.

# 8. Warehouse Process

Every donation gets inspected on arrival. Staff check quantity, expiry date, food category, and packaging condition, and correct any information the donor entered incorrectly before it's logged into inventory. Perishable items go into refrigerated storage as needed.

# 9. Food Distribution Process

Distribution follows First In, First Out (FIFO) whatever is closest to its expiry date goes out first. That keeps waste down and means families are consistently getting fresher food rather than whatever happens to be easiest to reach.

Families are registered before they receive anything, with a record that includes family ID, address, household size, ages, and any food allergies. Packages are then put together based on family size and monthly need.

# 10. Transportation

FoodShare currently runs two delivery trucks, used to pick up donations, move food between warehouses when needed, and support distribution runs. Routes under 50 km count as short haul; anything beyond that is long-haul.

# 11. Warehouses

The network has three warehouses, each holding donated food until it's distributed. All three include refrigerated storage for dairy and other temperature-sensitive items, along with a small safety stock set aside for emergencies or unexpected spikes in demand.

# 12. Stakeholders

| Stakeholder | Responsibility |
| --- | --- |
| Project Sponsor | Approves and supports the project |
| Project Manager | Plans and manages the project |
| Warehouse Manager | Manages warehouse operations |
| Warehouse Staff | Inspect and store donations |
| Delivery Drivers | Collect donated food |
| Volunteers | Help with sorting and packaging |
| Donors | Donate food items |
| Registered Families | Receive food assistance |
| Community Partners | Provide food donations and collection points |

# 13. Project Plan

## 13.1 Team Structure & Roles

The table below assigns each team member a primary role for the build phase. In practice everyone contributes across areas — this is a seven-person team building a full system in one semester — but having a named lead per area keeps ownership clear.

| Name | Role | Focus Area |
| --- | --- | --- |
| Dev Patel | Project Manager | Overall coordination, schedule, and sponsor liaison |
| Ebuka | Systems Analyst | Requirements gathering and process mapping |
| Vishal | Database Developer | Database design for donations, inventory, and family records |
| Om Surani | QA & Testing Lead | Test planning and defect tracking |
| Maharshi Darji | Business Analyst | Business case, benchmarking, and reporting |
| Rui Song | UI/UX Designer | Portal and dashboard screens for staff and partners |
| Hirva | Documentation Lead | Charter, user guides, and meeting records |

## 13.2 Timeline & Milestones

The milestones are organized into five phases running from Q3 2026 through Q3 2027, mirroring the phased rollout approach used by comparable food bank technology projects in this space.

| Phase | Target Window | Key Activities |
| --- | --- | --- |
| Requirements & Planning | Q3 2026 | Confirm scope with FoodShare staff; finalize database schema for donations, inventory, and family records; validate assumptions against warehouse and truck data. |
| Design & Core Database | Q3–Q4 2026 | Build the central database; design the donor and family registration modules; set up warehouse and inventory data structures. |
| Module Development | Q4 2026–Q1 2027 | Develop the donation portal, inventory management, transportation scheduling, and FIFO-based distribution logic. |
| Testing & Pilot | Q1–Q2 2027 | Run integration and user-acceptance testing; pilot the system at one warehouse before network-wide rollout. |
| Rollout, Training & Evaluation | Q2–Q3 2027 | Roll out to all three hubs; train staff and volunteers; deliver reports/dashboard; compile a Year 1 evaluation. |

## 13.3 Major Deliverables

- FoodShare central database

- Donor management module

- Family registration module

- Warehouse management module

- Inventory management module

- Transportation module

- Food distribution module (FIFO logic)

- Reports and dashboard

- User documentation and training materials

# 14. Reference Benchmarks: Comparable Network Operating Data

FoodShare doesn't yet capture structured, network-wide statistics the way a fully digitized food bank would — that's a large part of why this project exists. To ground our planning assumptions in something more solid than guesswork, we looked at the published operating data from Care Shield Food Bank, a food bank running the same three-hub footprint (Scarborough, Mississauga, North Bay). Care Shield is further along in its data maturity, so its numbers give a realistic picture of what a network at this scale looks like once it's fully instrumented — and a useful yardstick for FoodShare to plan against and, eventually, measure itself alongside.

## 14.1 Families & Community Reach

| Metric | Value |
| --- | --- |
| Total registered families | 1,000 |
| Total individuals supported | 4,557 |
| Average family size | 4.56 people |
| Adults / Children / Seniors | 45.0% / 35.5% / 19.5% |

| Hub | Families | Share |
| --- | --- | --- |
| North Bay | 352 | 35.2% |
| Scarborough | 326 | 32.6% |
| Mississauga | 322 | 32.2% |

## 14.2 Donor Network

| Metric | Value |
| --- | --- |
| Total active donor locations | 500 (100% active) |
| Mississauga / North Bay / Scarborough share | 35.8% / 33.2% / 31.0% |
| Largest single donor brand | 10.6% of donor base (two chains at 53 locations each) |
| Busiest pickup days | Wednesday and Friday (over 40% of scheduled pickups combined) |

## 14.3 Inventory & Storage

| Storage Type | SKUs Tracked | Stock on Hand |
| --- | --- | --- |
| Dry | 59 | 86,964 units |
| Cold | 19 | 24,697 units |
| Controlled (medical) | 13 | 21,028 units |
| Frozen | 9 | 14,568 units |
| Total | 100 | 147,257 units |

For reference, 6 of Care Shield's 100 tracked SKUs were running below reorder level at the time this data was captured — a reminder that reorder-alert logic (already planned as part of FoodShare's inventory module) earns its keep even at moderate scale.

## 14.4 Staffing & Volunteers

| Metric | Value |
| --- | --- |
| Full-time staff | 7 |
| Active volunteers | 25–50 (informal range) |

## 14.5 Transportation & Collection

| Metric | Value |
| --- | --- |
| Active delivery trucks | 2 |
| Operating days | Monday–Saturday, 08:00–16:00 |
| Scheduled pickup-days (annual) | 365 |
| Average crates collected per day | 45.0 |
| Total crates collected (annualized) | 16,435 |

## 14.6 Annual Operating Budget

| Category | Annual Cost (CAD) | Share |
| --- | --- | --- |
| Staff | $380,000 | 54.8% |
| Facility | $180,000 | 26.0% |
| Transportation | $48,500 | 7.0% |
| Operations | $21,600 | 3.1% |
| Contingency | $20,000 | 2.9% |
| Utilities | $18,000 | 2.6% |
| IT | $8,060 | 1.2% |
| Insurance | $8,000 | 1.2% |
| Marketing | $5,000 | 0.7% |
| Training | $4,000 | 0.6% |
| Total | $693,160 | 100% |

## 14.7 What This Means for FoodShare

A few things stand out once you line these numbers up against FoodShare's own operation. FoodShare currently runs the same two-truck, three-warehouse setup Care Shield started with, so the routing and storage pressures Care Shield eventually ran into — uneven pickup-day coverage between hubs, and a handful of SKUs slipping below reorder level — are realistic early warning signs for FoodShare to design around now rather than discover later. That's a big part of why FEFO tracking, per-warehouse inventory visibility, and a reporting dashboard are core deliverables here rather than nice-to-haves added after launch.

It's also a reasonable planning check on scale: a mature three-hub network in this size range tends to land somewhere around a few hundred thousand units of inventory on hand and tens of thousands of crates moved per year. FoodShare's system needs to be built to comfortably handle that range of volume, not just the smaller numbers the organization is working with today.

# 15. Project Assumptions

- FoodShare has three operational warehouses.

- Two delivery trucks are available throughout the project.

- Refrigerated storage is available for dairy and frozen products.

- Food donations are accepted only as food items, not money.

- Donors can either request pickup or deliver food directly to a warehouse.

- Partner organizations will regularly update donation information through the portal.

- Warehouse staff will verify every donation before it is stored.

- Perishable food will always be distributed first using the FEFO method.

- Food is distributed once every month to registered families.

- Family food packages are prepared according to household size.

- Enough volunteers are available to support warehouse operations.

# 16. Project Constraints

- Limited project budget.

- Only two delivery trucks are available.

- Limited warehouse storage capacity.

- Donations depend on community participation.

- Some food items have very short expiry dates.

- Volunteer availability may change throughout the year.

# 17. Project Risks

| Risk | Possible Solution |
| --- | --- |
| Food expires before distribution | Apply FEFO consistently and monitor expiry dates daily |
| Low number of donations | Build more partnerships with local businesses |
| Truck breakdown | Perform regular maintenance and keep a backup schedule |
| Inventory mistakes | Verify every donation before it's added to stock |
| Storage runs full | Move inventory between warehouses as needed |
| Uneven pickup coverage between hubs | Review route balance against per-hub demand, following the pattern observed in comparable networks (Section 14) |

# 18. Success Criteria

- Food donations are recorded correctly.

- Inventory information stays accurate.

- Food waste is reduced.

- Families receive food on time.

- Perishable food is distributed before expiry.

- Warehouse operations become more organized.

- Staff can generate reports whenever they're needed.

# 19. Future Improvements

Down the line, FoodShare could add more warehouse locations, expand the delivery fleet, bring on more community partners, and build a mobile app for donors and volunteers. The reporting layer built in this phase would also let the organization start spotting donation trends and shifting family needs earlier — the same way the benchmark data in Section 14 has helped shape this plan.

# 20. References

Care Shield Food Bank. (n.d.). Care Shield Food Bank. Retrieved July 22, 2026, from csfoodbank.com.

Care Shield Food Bank. (2026). Food Bank Complete Database [Internal organizational dataset: Families, Donors, Costing, Inventory, Staff, Transportation, and Collection Schedule records].

Food Banks Canada. (n.d.). HungerCount report. Food Banks Canada.

Project Management Institute. (2021). A guide to the project management body of knowledge (PMBOK guide) (7th ed.). Project Management Institute.

Note: this charter draws on Care Shield Food Bank's published operating figures strictly as a comparison benchmark for planning purposes. FoodShare's own donor, family, and inventory data will be captured independently once the system described here is in place.